## Sheet1
www.goodoldmanoj.com
Burn down chart
Project | Story | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
Pengenalan Albino | Story 1 | Pengertian albino | 3 | 3 | 0 | 0 | 0 | 0
| Story 1 | Penyebab albino | 3 | 3 | 3 | 5 | 2 | 0
| Story 1 | Gejala albino | 3 | 2 | 3 | 2 | 2 | 0
| Story 1 | Penyembuhan albino | 3 | 3 | 8 | 8 | 7 | 3
My Project | Story 2 | Task 2.2 | 8 | 8 | 8 | 8 | 8 | 7
My Project | Story 3 | Task 3.1 | 9 | 9 | 9 | 9 | 9 | 9
My Project | Story 3 | Task 3.2 | 5 | 5 | 5 | 5 | 5 | 5
My Project | Story 3 | Task 3.3 | 7 | 7 | 7 | 7 | 7 | 7
My Project | Story 3 | Task 3.4 | 3 | 3 | 3 | 3 | 3 | 3
My Project | Story 4 | Task 4.1 | 8 | 8 | 8 | 8 | 8 | 8
My Project | Story 4 | Task 4.2 | 6 | 6 | 6 | 6 | 6 | 6
My Project | Story 4 | Task 4.3 | 8 | 8 | 8 | 8 | 8 | 8
My Project | Story 4 | Task 4.4 | 9 | 9 | 9 | 9 | 9 | 9
Ideal - Remaining efforts in uninterrupted working hours |  |  | 75 | 67.5 | 60 | 52.5 | 45 | 37.5 | 30 | 22.5 | 15 | 7.5 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  | 75 | 74 | 77 | 78 | 74 | 65
Note on F5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on G5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered