## Sheet1
www.goodoldmanoj.com
Burn down chart
Project | Story | Task | Start | 2014-05-26 | 2014-05-27 | 2014-05-28 | 2014-05-29 | 2014-05-30 | 2014-05-31 | 2014-06-02 | 2014-06-03 | 2014-06-04 | 2014-06-05 | 2014-06-06 | 2014-06-07
Albino | Pengenalan Albino | Pengertian Albino | 6 | 6 | 0 | 0
|  | Penyebab Albino | 8 | 5 | 3 | 0
|  | Gejala Albino | 10 | 8 | 6 | 2 | 0
|  | Penyembuhan Albino | 8 | 5 | 3 | 1 | 0
| Kategori Albino | Albino Tirosinase Positif | 5 |  | 2 | 2 | 0
|  | Albino Tirosinase Negatif | 5 |  | 2 | 2 | 0
| Tipe Albino | Oculocutaneous Albinism | 6 | 3 | 1 | 0
|  | Ocular Albinism | 7 | 5 | 2 | 1 | 0
| Mitos Albino | Mitos Albino Pada Manusia | 3 |  |  |  | 1 | 0
|  | Mitos Albino Pada Hewan | 5 |  |  |  |  | 4 | 0
| Albino Pada Hewan | Pengantar Albino Pada Hewan | 8 |  |  |  | 7
|  | Mengidentifikasi Albino Pada Hewan | 8 |  |  |  | 7
Masalah Pada Hewan Albino
| Hewan Albino Terindah | 9 Hewan Albino Terindah | 8 | [5 empty] | 7 | 1
| Persilangan Albino | persilangan pada albino | 8 | [6 empty] | 5
| Tantangan Sosial | Tantangan sosial penderita albino | 10 |  |  |  | 8 | 5 | 3 | 2 | 1 | 0
| Legenda Albino di Indonesia | Albino di desa Mantar | 4 |  |  |  |  | 2 | 2 | 0
| Albino Pada Tanaman | Albino pada tanaman jagung | 3 | [7 empty] | 2 | 0
|  | Albino pada Redwood Tree | 3 | [8 empty] | 2 | 0
| Kelainan Mata pada Albino | Mata Silindris
Fotofobia
Strabismus
Nystagmus
Ambliopia
| Keindahan Alabino pada Manusia | Keindahan Alabino pada Manusia
| Ambliopia | Ambliopia Strabismik
Ambliopia Anisometric
Ambliopia Devripatif
Ideal - Remaining efforts in uninterrupted working hours |  |  | 115 | 103.5 | 92 | 80.5 | 69 | 57.5 | 46 | 34.5 | 23 | 11.5 | 0 | -11.5 | -23
Actual - Remaining efforts in uninterrupted working hours |  |  | 115 | 32 | 19 | 8 | 23 | 11 | 7 | 6
Note on F5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on G5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered