## Sheet1
www.goodoldmanoj.com
Burn down chart
Project | Story | Task | Start | 2014-05-26 | 2014-05-27 | 2014-05-28 | 2014-05-29 | 2014-05-30 | 2014-05-31 | 2014-06-02 | 2014-06-03 | 2014-06-04 | 2014-06-05 | 2014-06-06 | 2014-06-07
Albino | Pengenalan Albino | Pengertian Albino | 6 | 6 | 0
|  | Penyebab Albino | 8 | 5 | 3 | 0
|  | Gejala Albino | 10 | 8 | 6 | 2 | 0
|  | Penyembuhan Albino | 8 | 5 | 3 | 1 | 0
| Kategori Albino | Albino Tirosinase Positif | 8 |  | 8 | 0
|  | Albino Tirosinase Negatif | 7 |  | 7 | 0
| Tipe Albino | Oculocutaneous Albinism | 6 |  | 6 | 0
|  | Ocular Albinism | 7 | 5 | 2 | 1 | 0
| Mitos Albino | Mitos Albino Pada Manusia | 3 |  |  |  | 1 | 0
|  | Mitos Albino Pada Hewan | 5 |  |  |  |  | 4 | 0
| Albino Pada Hewan | Pengantar Albino Pada Hewan | 8 |  |  |  | 7
|  | Mengidentifikasi Albino Pada Hewan | 8 |  |  |  | 7
|  | Masalah Pada Hewan Albino | 8 |  |  |  | 4 | 2 | 1 | 0
| Hewan Albino Terindah | 9 Hewan Albino Terindah | 8 | [5 empty] | 7 | 1 | 0
| Persilangan Albino | Persilangan Pada Albino | 8 | [6 empty] | 8 | 0
| Kelainan Mata Albino | Nystagmus | 6 | [6 empty] | 6 | 0
|  | Strabismus | 8 | [7 empty] | 6
|  | Fotosentivitas | [8 empty] | 7
|  | Mata Silindris (Astigmatism) | 7 | [7 empty] | 5
| Albino Pada Tanaman | Albino Pada Tanaman | 8 | [7 empty] | 6
|  | Reed Wood Tree Albino | 6 | [7 empty] | 4
Ideal - Remaining efforts in uninterrupted working hours |  |  | 143 | 128.7 | 114.4 | 100.1 | 85.8 | 71.5 | 57.2 | 42.9 | 28.6 | 14.3 | 0 | -14.3 | -28.6
Actual - Remaining efforts in uninterrupted working hours |  |  | 143 | 29 | 35 | 4 | 19 | 6 | 8 | 15 | 28
Note on F5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on G5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered